## Test Plan
S.No | Resource Name | Functional Requirement | Test Objective | Scope of Testing | Test Strategy/Approach | Test Environment | Test Schedule & Milestones | Roles & Responsibilities | Entry Criteria | Exit Criteria | Risks & Mitigation
1 | Shivam Negi | System end to end | Comlete End to End Automation testing | Signup,Login,Cart,Checkout | Selenium Automation Testing | Chrome v110, Windows 11, testdata.xslx | 10-11-2025 to 22-11-2025 | Prepare & execute automaton test cases | Automation test cases ready to execute | Complete flow end to end tested through automation | Automation code may contain bug itself

## RTM
FR ID | FR DESCRIPTION | TC ID | Defect ID
SIGNUP_01 | Complete testing with automation of signup page | REG-01-12 | REG-07-09
LOG_02 | Complete testing with automation of login page | LOGIN-01-07 | N/A
CRT_03 | Complete testing with automation of cart page | CART-01-07 | N/A
CHKT_04 | Complete testing with automation of checlout page | CHECKOUT-01-05 | N/A

## TestCases
ID | Test Scenario | Precondition | StepsExpected | Test Data | Expected Result | Acttual Outcome | Priority | Status
REG-01 | Verify Sign up Navigation from Home Page | 1.Website is live 2.Signup Link is available | 1.Open the Website / Home Page 2.Click SignUp/Login link 3.Verify the navigation to signup/login page | src/test/resources/testData.xslx | Navigated to Sign Up page | 1.Navigated successfully to Signuo/Login Page | High | Pass
REG-02 | Verify Name,Email field and Signup bitton is displayed | 1.Sign up Page is available | 1.Open the Sign up Page. 2.Verify the fields are displayed | src/test/resources/testData.xslx | All fields are displaying | 1.All fields are displaying correctly. | High | Pass
REG-03 | User Registration (Positive) | 1.Sign up Page is available | 1. Open registration page 2.Enter valid name, unique email 3.Click Signup Button. 4.fill complete form with valid data. 5.Click Create Account | src/test/resources/testData.xslx | Account created; redirected to Home Page | Account created and redirected to Home Page | High | Pass
REG-04 | User Registration with different data | 1.Sign up Page is available | 1. Open registration page 2.Enter valid name, unique email 3.Click Signup Button. 4.fill complete form with valid data. 5.Click Create Account | src/test/resources/testData.xslx | Account created; redirected to Home Page | Account created and redirected to Home Page | High | Pass
REG-05 | verify Registration should not ne possible with verify with very long name | 1.Sign up Page is available | 1. Open registration page 2.Enter very long name, unique email 3.Click Signup Button. 4.fill complete form with valid data. 5.Click Create Account | src/test/resources/testData.xslx | Account should no be created and error message is shown | Account created and no error message is shown | Low | Fail
REG-06 | Registration with Blank Fields | 1.Sign up Page is available | 1. Open registration page 2.Enter name, unique email 3.Click Signup Button. 4.fill complete form with missing data. 5.Click Create Account | src/test/resources/testData.xslx | Error message(s) for each blank required field | Error message(s) for each blank required field | High | Pass
REG-07 | Registration with Invalid Email | 1.Sign up Page is available | 1. Open registration page 2.Enter valid name, invalid email, password, confirm password 3.Submit | src/test/resources/testData.xslx | Validation message: "Please include an '@' in the email address. 'invalid-email-format' is missing an '@'" | Validation message: "Please include an '@' in the email address. 'invalid-email-format' is missing an '@'" | Medium | Pass
REG-08 | Verify Unicode Support for the sign up | 1.Sign up Page is available | 1. Open registration page 2.Filli signup form with Name: Unicode 用户, Email: unicode.user@example.com 3.Submit | src/test/resources/testData.xslx | Account created; redirected to Home Page | Account created; redirected to Home Page | Medium | Pass
REG-09 | Verify secure sign up with sql injection protection | 1.Sign up Page is available | 1. Open registration page 2.Fill signup form with Name: SQLInjection';--, Email: sql.injection@example.com 3.Submit | src/test/resources/testData.xslx | Error message: "invalid name" | Account created; redirected to Home Page | Medium | Fail
REG-10 | Verify empty name and email field | 1.Sign up Page is available | 1. Open registration page 2.Click the SignUp button without filling | src/test/resources/testData.xslx | Validatioin message: "Fillout this field" | Validatioin message: "Fillout this field" is shown | Low | Pass
REG-11 | Verify again login with valid credentials | 1.Sign up Page is available | 1. Open registration page 2.Enter valid name, unique email 3.Click Signup Button. 4.fill complete form with valid data. 5.Click Create Account | src/test/resources/testData.xslx | Account created; redirected to Home Page | Account created and redirected to Home Page | Low | Pass
REG-12 | Registration with Duplicate Email | 1.Sign up Page is available 2.Email is already registered | 1. Open registration page 2.Enter valid name, existing email, password, confirm password 3.Submit | src/test/resources/testData.xslx | Error message: "Email already in use"; user remains on registration page | Error message: "Email already in use"; user remains on registration page | High | Pass
LOGIN-01 | Verify Login Navigation from Home Page | 1.Website is live 2.Login Link is available | 1.Open the Website / Home Page 2.Click SignUp/Login link 3.Verify the navigation to signup/login page | N/A | Navigated to Login page | Navigated successfully to Login page | High | Pass
LOGIN-02 | Verify all login form elements are displayed and functional | 1.Website is live 2.Login Page is available | Step 1: Open the Login Page Step 2: Verify Email Input Field Step 3: Verify Password Input Field Step 4: Verify Login Button Step 5: Validating all login element | N/A | All fields are displaying | All fields are displaying | High | Pass
LOGIN-03 | Verify login with valid credentials | 1.Website is live 2.Login Page is available | Step 1: Open the Login Page Step 2: Enter valid Login Credentials Step 3: Click login button | src/test/resources/testData.xslx | Login success navigated to Dashboard | Login success navigated to Dashboard | High | Pass
LOGIN-04 | Verify login with wrong password | 1.Website is live 2.Login Page is available | Step 1: Open the Login Page Step 2: Enter valid Login Credentials with wrong password Step 3: Click login button | src/test/resources/testData.xslx | Login Fail with error:"Your email or Password is incorrect" | Login Fail with error:"Your email or Password is incorrect" | High | Pass
LOGIN-05 | Verify login with wrong email | 1.Website is live 2.Login Page is available | Step 1: Open the Login Page Step 2: Enter valid Login Credentials with wrong email Step 3: Click login button | src/test/resources/testData.xslx | Login Fail with error:"Your email or Password is incorrect" | Login Fail with error:"Your email or Password is incorrect" | High | Pass
LOGIN-06 | Verify login with invalid email format | 1.Website is live 2.Login Page is available | Step 1: Open the Login Page Step 2: Enter valid Login Credentials with invalid email format Step 3: Click login button | src/test/resources/testData.xslx | Validation message: "Please include an '@' in the email address. 'invalid-email-format' is missing an '@'" | Validation message: "Please include an '@' in the email address. 'invalid-email-format' is missing an '@'" | Medium | Pass
LOGIN-07 | Verify login with subaddressing email format | 1.Website is live 2.Login Page is available | Step 1: Open the Login Page Step 2: Enter valid Login Credentials with subaddressing email format Step 3: Click login button | src/test/resources/testData.xslx | Login success navigated to Dashboard | Login success navigated to Dashboard | Low | Pass
CART-01 | Verify navigation from home page to products page | 1.Website is live 2.Products page Link is available | 1.Open the Website / Home Page 2.Click Products link 3.Verify the navigation to signup/login page | N/A | Navigated to Products page | Navigated successfully to Products page | High | Pass
CART-02 | Verify product can be added to cart successfully | 1.Website is live 2.Products page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Click Add to Cart button | N/A | Cart Modal is shown with message:Your Product has been added to the cart | Cart Modal is shown with message:Your Product has been added to the cart | High | Pass
CART-03 | Verify Added product to cart appears in cart page | 1.Website is live 2.Products page is available 3.Cart Page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Navigate to Cart Page Step 4:Verify Product Exists in Cart | N/A | Product ID 1 verification result: Found | Product ID 1 verification result: Found | High | Pass
CART-04 | Verify item can be removed from cart successfully | 1.Website is live 2.Products page is available 3.Cart Page is available | Step 1: Open the Products Page Step 2: Add Product with id:2 Step 3: Navigate to Cart Page Step 4:Verify Product Exists in Cart Step 5: Removing Product from Cart Step 6: Verify Product Removed from Cart | N/A | Item successfully removed from cart | Item successfully removed from cart | High | Pass
CART-05 | Verify product quantity is displayed correctly in car | 1.Website is live 2.Products page is available 3.Cart Page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Navigate to Cart Page Step 4:Retrieving Product Quantity Step 5: Verify Specific Quantity Value | N/A | Expected quantity: 1 | Expected quantity: 1 | Medium | Pass
CART-06 | Verify cart displays correct pricing information | 1.Website is live 2.Products page is available 3.Cart Page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Navigate to Cart Page Step 4:Retrieving Product Price Step 5: Validate price Step6: Validate Total Calculated | N/A | Expected Price and Total Price: 500,500 | Actual Price and Total Price: 500,500 | Medium | Pass
CART-07 | Verify user cannot proceed from cart to checkout page without login | 1.Website is live 2.Products page is available 3.Cart Page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Navigate to Cart Page Step 4:Verify Product in the cart Step 5: Click Proceed to checkout Step6: Verify Modal Display | N/A | Checkout modal displayed for guest user | Checkout modal displayed for guest user | Medium | Pass
CHECKOUT-01 | Verify logged-in user can navigate to checkout page | 1.Website is live 2.Products page is available 3.Cart Page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Navigate to Cart Page Step 4:Verify Product in the cart Step 5: Click Proceed to checkout Step6: Verify Checkout Page | N/A | Successfully navigated to checkout page | Successfully navigated to checkout page | High | Pass
CHECKOUT-02 | Verify user can add order comment and proceed to payment | 1.Website is live 2.Products page is available 3.Cart Page is available 4.Checkout Page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Navigate to Cart Page Step 4:Verify Product in the cart Step 5: Click Proceed to checkout Step6: Add Comment to the order comment:'Please deliver between 9 AM to 5 PM' Step 7: Click Place Order button Step 8: Verify Payment from Display | N/A | Successfully placed order and navigated to payment | Successfully placed order and navigated to payment | Low | Pass
CHECKOUT-03 | Verify user can fill payment details in checkout | 1.Website is live 2.Products page is available 3.Cart Page is available 4.Checkout Page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Navigate to Cart Page Step 4:Verify Product in the cart Step 5: Click Proceed to checkout Step6: Add Comment to the order comment:'Please deliver between 9 AM to 5 PM' Step 7: Click Place Order button Step 8: Verify Payment from Display Step9: Enter card details Step10 : Click the payment button | N/A | All payment fields filled successfully | All payment fields filled successfully | High | Pass
CHECKOUT-04 | Verify complete end-to-end order placement with payment | 1.Website is live 2.Products page is available 3.Cart Page is available 4.Checkout Page is available | Step 1: Open the Products Page Step 2: Add Product with id:1 Step 3: Navigate to Cart Page Step 4:Verify Product in the cart Step 5: Click Proceed to checkout Step6: Add Comment to the order comment:'Please deliver between 9 AM to 5 PM' Step 7: Click Place Order button Step 8: Verify Payment from Display Step9: Enter card details Step10 : Click the payment button | N/A | Order placed successfully | Order placed successfully | High | Pass
CHECKOUT-05 | Verify complete end-to-end order placement with tab switching | 1.Website is live 2.Products page is available 3.Cart Page is available 4.Checkout Page is available | Step 1: Perform User Login Step 2: Navigate to Products Page Step 3: Open Product in Current Tab Step 4: View Cart Step 5: Verify Product in Cart (Tab 1) Step 6: Open Products Page in New Tab Step 7: Add Product in New Tab Step 8: Verify Both Products in Cart (Tab 2) Step 9: Switch Back to Original Tab Step 10: Refresh Cart in Original Tab Step 11: Proceed to Checkout from Original Tab Step 12: Verify Checkout Page Display Step 13: Switch to Second Tab and Closing It Step 14: Switch Back to Original Tab | N/A | Successfully completed tab switching test with checkout | Successfully completed tab switching test with checkout | Medium | Pass

## Defect_Report
DEFECT_ID | Test Scenario |  | Precondition | StepsExpected | Test Data | Expected Result | Acttual Outcome | Priority | Status
DEF_01 | verify Registration should not ne possible with verify with very long name | REG-07 | 1.Sign up Page is available | 1. Open registration page 2.Enter very long name, unique email 3.Click Signup Button. 4.fill complete form with valid data. 5.Click Create Account | src/test/resources/testData.xslx | Account should no be created and error message is shown | Account created and no error message is shown | Low | Fail
DEF_02 | Verify secure sign up with sql injection protection | REG-09 | 1.Sign up Page is available | 1. Open registration page 2.Fill signup form with Name: SQLInjection';--, Email: sql.injection@example.com 3.Submit | src/test/resources/testData.xslx | Error message: "invalid name" | Account created; redirected to Home Page | Medium | Fail

## Test Execution Summary
BASIC INFORMATION
PROJECT NAME | C4 Project - E-commerce Application
MODULE | Sign up, Login,Cart, Checkout
TEST CYCLE | Sprint 1 - Selenium Automation testing
PREPARED BY | QA Team Lead - Shivam Negi
START DATE | 2025-10-11
END DATE | 22-11-2025
TEST CASE EXECUTION SUMMARY
TOTAL TC | 31
EXECUTED | 31
PASSED | 29
FAILED | 2
BLOCKED | 0
TBD | 0
PASS PERCENTAGE | 93.55%
FAIL PERCENTAGE | 6.452%
EXECUTION STATUS BY REQ/SCEN
TC_ID | TS DESC | EXECUTED | PASSED | FAILED | BLOCKED | TBD
REG-01-12 | User Registration | 12 | 10 | 2 | 0 | 0
LOGIN-01-07 | User Login | 7 | 7 | 0 | 0 | 0
CART-01-07 | Cart Functionaloity | 7 | 7 | 0 | 0 | 0
CHECKOUT-01-05 | Checkout Functionality | 5 | 5 | 0 | 0 | 0
DEFECT SUMMARY
TOTAL DEFECTS | 2
TOTAL P1 | 0
TOTAL P2 | 0
TOTAL P3 | 2
TOTAL P4 | 0
TOTAL P5 | 0
FIXED | 0
NOT FIXED | 0
OPEN | 0
NEW | 2
HOLD | 0
FIXED PERCENTAGE | 0%
NOT FIXED PERCENTAGE | 100%